## Project Management Questions
Project Approach Questionnaire (PAQ)
Project: |  |  |  | Name:
Date: |  |  |  | Position:
|  | Indicate the closest collective opinon |  |  |  |  | Where appropriate, comment on issues or risks related to a more negative response to this aspect of the DSDM approach
Ref | Statement | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree
1 | All members of the project understand and accept the DSDM approach (Philosophy, Principles and Practices)
2 | The Business Sponsor and the Business Visionary demonstrate clear and proactive ownership of the project.
3 | The business vision driving the project is clearly stated and understood by all members of the project team
4 | All project participants understand and accept that on-time delivery of an acceptable solution is the primary measure of success for the project
5 | The requirements can be prioritised and there is confidence that cost and time commitments can be met by flexing the scope of what's delivered.
6 | All members of the project team accept that requirements should only be defined at a high level in the early phases of the project and that detail will emerge as development progresses.
7 | All members of the project team accept that change in requirements is inevitable and that it is only by embracing change that the right solution will be delivered.
8 | The Business Sponsor and Business Visionary understand that active business involvement is essential and have the willingness and authority to commit appropriate business resources to the project.
9 | It is possible for the business and solution development members of the Solution Development Team to work collaboratively throughout the project.
10 | Empowerment of all members of the Solution Development Teaam is appropriate and sufficient to support the day-to-day decision-making needed to rapidly evolve the solution in short, focussed Timeboxes
11 | The DSDM roles and responsibilities are appropriately allocated and all role holders understand and accept the responsibilities associated with their role.
12 | The Solution Development team has the appropriate collective knowledge and skills (soft skills and technical skills) to collaboratively evolve an optimal business solution.
13 | Solution Development Team members are allocated to the project at an appropriate and consistent level sufficient to fully support the DSDM timeboxing practice
14 | Tools and collaborative working practices within the Solution Development Team are sufficient to allow effective Iterative Development of the solution.
15 | All necessary review and testing activity is fully integrated within the Iterative Development practice.
16 | Project progress is measured primarily through the incremental, demonstrable delivery of business value.
17 | There are no mandatory standards or other constraints in place that will prevent the application of the DSDM Philosophy and Practices on this project.
General comments on suitability or risk associated with the DSDM approach:
©Agile Business Consortium 2019
Note on H6: A project team will not function effectively if they do not understand DSDM, or are not given appropriate support. Organise training and briefings as required.
Note on H7: There is no work-around for a weakness in business ownership and vision. If all engagement efforts fail, the only option is to make it clear that the solution delivered will not have business input and will be determined by the Solution Development team. This may force engagement.
Note on H8: Without common understanding of a clear vision, there is a risk that time will be wasted on things with little value.Speak to the Visionary, or arrange for him/her to share their vision. Place a simple poster in the Team area to ensure the vision is visible to all. Use the Vision by asking questions such as : "Does what we are doing move us closer to achieving the vision"?
Note on H9: Focusses everyone on the business drivers and on-time delivery. Also discourages a quest for perfection. If no genuine deadline exists, use the PRL and estimates to derive a delivery plan that creates a target end-date.
Note on H10: Challenge priorities to ensure they are realistic. Decompose requirements to create lower priority ones if possible. If insufficient feature-contingency exists, create time-contingency by adding one or more 'contingency' timeboxes to the plan.
Note on H11: Defining detail too early risks it being inaccurate when work starts, does not allow the correct solution to evolve, and imposes a change-control overhead. Hold discussions with the team on why this is important. Ensure that requirements capture the business need and not an implied or suggested solution.
Note on H12: The Solution Development team needs to embrace change in order to deliver the optimum solution. If the commercial reality is "fixed price for fixed specification" the client should prioritise the requirements, and provide the supplier with timeboxed 'work packages'. Any changes needed should be able to be traded off against work planned for later.
Note on H13: If the business members of the team are not always available, negotiate times when they will be available.If even this is not possible, consider the "Specification-led" approach (see white paper at dsdm.org)
Note on H14: 'Instant access' to business roles minimises the risk of the solution evolving in the wrong way, and ideally business and technical roles should be co-located. If access to business resources is limited, structure the timebox to maximise the use of available business time. Consider modelling and other communication tools to assist
Note on H15: Empowerment is essential in order to avoid decisions being delayed or over-ridden. Encourage senior authorities to play a more active role, while gradually delegating more authority.
Note on H16: Consider specific training or workshops to clarify roles and responsibilities. Ensure a good fit of each person to the role. It is possible to transfer some responsibilities between roles if necessary but if one or more roles is unfulfilled, escalate to the Sponsor to resolve.
Note on H17: Ideally, solution roles will be technically multi-skilled but if not, they must be able to support each other. Ensure all required skills are available within the team when needed. Avoid putting a single one-man 10-day task into a 10-day timebox; break it down or share it.
Note on H18: By default Solution Development team members should be allocated to the project full time, or at least the project should be their top priority. If not, secure formal agreements as to when their time will be spent on the project, synchronising with other team members to allow collaborative working. Beware of over-commitment and optimistic estimates. If resourcing is very unpredictable, avoid committing to a delivery date, and make the work as granular as possible.
Note on H19: Encourage face-to-face communication whenever possible. The practices of Workshops and Modelling play a significant role here. Where the team is not co-located, utilise technology to maximise the ease of communication and collaboration between team-members.
Note on H20: The aim is to deliver fully-tested solution increments at the end of each timebox, so reviews and testing should be a part of each timebox. This must be planned for, and Solution Testers involved as early as possible. If integrated testing is not possible, set up a parallel stream for testing so that the output from a development timebox is the input to a testing one. Ensure that the development team do appropriate testing themselves, though.
Note on H21: Primary output of each timebox should be a demonstrable increment of the Evolving Solution. Be creative about what can be demonstrated if it's not obvious. Get the Solution development team to demonstrate the solution to each user story completed in each timebox, with the Ambassador or Visionary formally 'accepting' what has been done.
Note on H22: Avoid commercial agreements that include a 'fixed specification', which exaggerates the risks associated with a Waterfall approach. Ensure the Procurement team understand DSDM Philosophy, Principles and Practices. Ensure that an incremental approach to installation of technical environments and to deployment is acceptable, and that all support functions are in agreement with the project approach.